## Deliverables
The Engineer Accelerator
Deliverables Tracking
2016-07-20 | Done | 2016-07-27 | Done | 2016-08-03 | Done | 2016-08-14 | Done | 2016-08-21 | Done | 2016-08-29 | Done | 2016-09-08 | Done
Task Enumeration (Task List Google Sheet) | Done | Quick Start Issue List | Done | Hardware Block Diagram | Done | Hardware Block Diagram | Done | Update Architecture Documents | Done | Update Product Architecture Spreadsheet to match issue list | Done | Generate a Bitstream using Daniels Vivado Project | Done
Setup Development Environment (Win 10) | Done | Snickerdoodle Book Issue List | Done | Major Signals List | Not Done | Major Signals List | Done | Define Bring Up Test for each system block | Done | Add spcecifity to Bring Up Test spreadsheet | Done | Load Bitstream into Snickerdoodle | Done
Kick Off Call | Done | Wireless Connection Guide Issue List | Done | Pinouts | Done | Pinouts | Done | Control Logic to OV7670 block implemented in HW and firmware | Not Done | Continue with implementation of Control Logic to OV7670 block | Still working on this | Verify if camera images are being sent to a monitor | Not Done
Parts Check | Done | Hardware Configuration Guide | Done | Calculations | Not Done | Calculations | Did not need | Update Task list with new estimates for rest of block | Done
[6 empty] | Rework of Task List to incorporate per system block tasks | Done
8/03/16 (2 weeks after kickoff) | Done
Send Annotated Book and User guide to Krtkl team
Create and Send video of working Snickerdoodle to Malcolm